## LMS issues
Issue | Description | TAT | Remarks | Comments by Gitesh
Login Errors | There is no error message when incorrect login credentials (ID/password) are entered. Ideally, an error message should be displayed in this scenario. | 25th April
Course View in Backend | The "View Courses" option should be displayed in icon format in the backend as well. | 25th April
Quiz Module | Timer Missing: There is no timer in the quiz, which is crucial for timed assessments. | Done
| Answer Selection: It's difficult to confirm if an answer has been selected or not. A visual indication (such as a punch hole style) would make it easier to differentiate between selected and unselected options. It is also inconsistent across the courses | Done
| Answer Rationale: The rationale for the correct answer should be provided after the user submits their answer | 25th April | This is a data entry point. For Official sample papers there are rationale. for Exam simulator where we have made the quizzes, there is no rationale, just right wrong
Course Progress and Completion | The system does not show completed modules or progress towards completion. A progress tracking feature is needed | 25th April
Sample Exam Questions | The sample exam questions should be displayed one at a time, with "Submit" and "Next" buttons, along with a timer and an option to review the answers at the end with a summary view. |  | This is nice to have, but not mandatory
Final Submission Button | A "Final Submission" button should be added to ensure users can confirm and submit their exam. | 25th April
Automated Emails | Students should receive an automated email after course creation with course details and login information sent to their registered email address. | 25th April
ITIL Exam Simulators | The ITIL v4 Foundation Exam Simulator is not working | Done | ??? This is priority 1 This has to work.
| The ITIL CDS Exam Simulator is also not functioning correctly | Quention back need to be put in desired format to be shared by Ducis 25th April
Issue with all the courses exam simulators as there are now working or very inconsistent
Module Alignment Issues | ITIL HVIT module is completely misaligned and needs to be re-uploaded
Module Headings are missing in all courses, which affects navigation and clarity
| ITIL DPI Module 6 is not working in the new LMS | 25th April
ITIL DSV Module is completely mismatched and needs to be re-uploaded
Points added by Sunil Sir
E-Reader – Global search for terms instead of page / page
How do we get rational in the exam simulator
Can we do direct entry of questions and answers (in addition to file upload) of questions
Quiz’s will have to be structured as per category
Link from Website to to Mock test for LMS
Options for flagging questions / submit / are you sure / final submit
Bookmarks for elearning missing – to resume learning from where you last left.
Dashboard View for learner of scores in mock tests, and courses completed.

## Website & Ecommerce
Issue | Descriotion TAT | TAT | Remarks | Comments by Gitesh
Training and Certification Section | There is currently no visible call-to-action (CTA) in the Training and Certification section.
Inconsistent Font Usage | The font style and size are inconsistent across different pages (some texts are too large, others too small)
ATVA Acronym | The acronym "ATVA" is used without any explanation, leading to ambiguity about its meaning |  | This is for us to explain. If Gitesh, gives access to how to modify through dgapp, we will make changes ourselves
Exclusive Tool Vendor Highlight | Exclusive tool vendors are not prominently featured or highlighted |  | This is for us to explain. If Gitesh, gives access to how to modify through dgapp, we will make changes ourselves
"Stats" Terminology | The term "Stats" appears to be jargon and may not be clear to all users.
Shop Section | The shop section is currently on the same page as other content,Create a separate page for the shop and include organized sections such as Training, Exam Vouchers, Consulting, Mock Tests, and Case Studies |  | The Shop page has to be redone. let us complete the other points on the excel and then look at this on the 10/15 April
Blog Section | The blog section is not clearly separated, Please create a dedicated Blog page to ensure better navigation and user experience
Bulk Upload/Download Functionality: | The bulk upload and download feature for the open batch schedule is not functioning properly. |  | Priority 1
Login Requirement for Purchases | The website prompts users to log in before purchasing, though this is unnecessary for guest users,Allow users to continue with their purchases as guests without requiring them to log in |  | This is a design issue, not at all happy with the ecommerce design and layout. Seperate discussion required for this
Calendar Layout | The calendar is too long and lacks organization,Break the calendar into monthly sections for better user experience and navigation |  | Good Idea.
Mock Test Integration | The mock test section still redirects users to the old LMS website instead of the new one |  | ???? - Priorty 1
Delayed Leads in “Get in Touch” | Leads generated through the "Get in Touch" form are delayed in being entered into the system
Course Images Compliance | The course images are not in compliance with PeopleCert’s intellectual property protocols, which could lead to potential legal issues. |  | This is also urgent. How do we edit using DG app. This is a compliance issue
Blog Articles | The blog articles section is a good source of engagement, but there’s no clear mechanism for adding new articles
Case Studies | Case studies are currently listed but there is no option to add new ones,The ability to add, modify, or update course information (including logos) is limited.
Factsheets/Course Outlines | There is no clear method to add new courses or update old ones
Guidelines/FAQ Page | The FAQ page is currently non-functional
Visitor Data Tracking | There is no clear way to capture or view visitor data, which impacts SEO tracking